## 10-14-24
Security Steering Committee
Date/Time: October 14, 24
Attendance: Caitlin, Zack, Mark, Alasdair, Cheryl, Jasmine
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Mark | Need to decide which MOAB courses to roll out and when | Alasdair/Cheryl to look into legal requirements for all staff .. Jasmine going to share materials with Zack for Fam Med
Patient Termination Check List | Zack | Zack bringing the checklist to the admin team. Further discussion here?
Security Supervisor/Guards Recruitment | Alasdair | Complete 24/7 staffing hired. Last person starts 11/4
Security Supervisor Move to A1 Window | Alasdair | Larry is now working at the ED triage window unless he needs to be in the A1 office for privacy
Patient/Visitor/Staff Violence Events | Team | One in the ED 9/17
MLPD/Mono County Sherrif Collaboration | Alasdair | Reviewing the MOU and Flock | Cheryl has started the review. Caitlin/Jasmine also reviewing
Incident reporting | Security team | Since need to track all incidents, and Verge has existing stigma, have all incidents sent to security, who can follow up as well as add to Verge | Lenna working with Verge on re-doing the system.
MH Weapons Policy | Alasdair | Can we improve signage? What about patients brought in by Mono County EMS | Alasdair to discuss with Chief Bullock of Mono County EMS to find out what their policy is prior to bringing patients to the ED
Psychiatric Emergency Team | Caitlin/Cheryl | Met with Mono County BH | Another meeting scheduled in November
Safe Sitter Program Status | Jasmine | Jasmine unable to attend for update this week | Policy needs to be completed prior to sitter education
5150/1799 Holds | Jasmine | Jasmine unable to attend for update this week | Still finalizing policies
Panic Buttons for ED Providers | Alasdair/Mark | Alasdair working on setting up sales calls | Perhaps we consider it as a role-based device rather than for individuals
EMTALA | Cheryl |  | Cheryl going over findings with Jasmine/Caitlin next week