## 10-14-24
Security Steering Committee
Date/Time: April 23, 25
Attendance: Caitlin, Zack, Mark, Alasdair, Jasmine, Larry, Ric
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Alasdair | Jen Goodman and her team are now trained to do the 4-hour MOAB training to front office staff
Patient/Visitor/Staff Violence Events | Team | 3 events this month | Panic button locations need to be checked
MLPD/Mono County Sherrif Collaboration | Jasmine / Ric | Still working on MOU. | Jasmine has asked Caitlin to take over the negotiations.
MH Weapons Policy | Alasdair | 6 new signs around facility. Waiting to hear back from Mono County legal department about what they're willing to do r.e. their policies
Psychiatric Emergency Team | Caitlin | Met with Mono County BH | November meeting had to be cancelled. Trying to reschedule next year
Safe Sitter Program Status | Jasmine | Can meet the need in the ED with current staffing. | Policy has been re-written.
5150/1799 Holds | Jasmine | 5150 policy sent out to other floor managers for review. Up to date on audits | trying to set up quarterly/monthly meeting with Mono County BH and MLPD for debrief
Panic Buttons for ED Providers | Alasdair/Mark | Quote from 911Cellular is $14200. Plan is to request it in next year's budget
Lockdown Procedures | Maintenance | The existing buttons lockdown the hospital, but not everything on campus | Only security/Jeff/Admin can lockdown further buildings. Need a policy
Panic Button Alerts | Alasdair | Jeff has changed the panic button in Bishop so that it no longer has an audible alarm | Jeff still needs to finish this.
Metal detectors | Mark/Alasdair | Met with Metrasens about their weapon detectors - one detector is $17500 plus $1800 install | Again - targetting next FY budget
New Business
Do we need to keep meeting quarterly | Alasdair | Suggestion to go to an ad-hoc basis | Especially with Security now fully staffed. General consensus is to keep quarterly meetings
Security Assessment | Mark | Should we consider doing a new security assessment? A recommendation from John White | Caitlin is going to reach out to Beta to see if they have a free assessment
Metrics | Mark | Should we set metrics to measure success of the program? | We're currently looking at security monthly/daily reports, verge. Ask Beta what they measure. Clarivate
House Sup Phone | Jasmine/Alasdair | We're getting a new phone for the night supervisor to make it easier to get in touch with them