## 10-14-24
Security Steering Committee
Date/Time: October 28, 24
Attendance: Caitlin, Zack, Mark, Alasdair, Cheryl, Jasmine, Larry
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Alasdair | Cheryl looking in to OSHA requirements
Patient Termination Check List | Zack | Zack bringing the checklist to the admin team. Further discussion here? | Leaving to the admin team
Security Supervisor/Guards Recruitment | Alasdair | Complete 24/7 staffing hired. Last person starts 11/4
Security Supervisor Move to A1 Window | Alasdair | Larry is now working at the ED triage window unless he needs to be in the A1 office for privacy | Can we look into shifting the current staffing to cover the gaps when there is no PD? Addiontal ask of having someone in the ED window for this week.
Patient/Visitor/Staff Violence Events | Team | 4 incidents reported
MLPD/Mono County Sherrif Collaboration | Alasdair | Reviewing the MOU and Flock | Revise with 5150 holds as well
Incident reporting | Security team | Lenna working with Verge on re-doing the system | Security guards to have their own report any time they are requested to respond
MH Weapons Policy | Alasdair | Ordered new Signs | ED has new envelopes for patient valuables (and weapons)
Psychiatric Emergency Team | Caitlin/Cheryl | Met with Mono County BH | Another meeting scheduled in November
Safe Sitter Program Status | Jasmine | Jasmine unable to attend for update this week | Policy needs to be completed prior to sitter education
5150/1799 Holds | Jasmine | Jasmine unable to attend for update this week | Still finalizing policies
Panic Buttons for ED Providers | Alasdair/Mark | Alasdair working on setting up sales calls | Perhaps we consider it as a role-based device rather than for individuals
EMTALA | Cheryl |  | Cheryl/Caitlin/Jasmine to walk through tomorrow