## 10-14-24
Security Steering Committee
Date/Time: October 28, 24
Attendance: Caitlin, Zack, Mark, Alasdair, Cheryl, Jasmine, Larry
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Alasdair | Cheryl looking in to OSHA requirements
Patient Termination Check List | Zack | Zack bringing the checklist to the admin team. Further discussion here? | Leaving to the admin team. Remove for next meeting
Security Supervisor/Guards Recruitment | Alasdair | Complete 24/7 staffing hired. Last person starts 11/4
Security Supervisor Move to A1 Window | Alasdair | Larry is now working at the ED triage window unless he needs to be in the A1 office for privacy | Remove for next meeting. This is complete
Patient/Visitor/Staff Violence Events | Team | 4 incidents this month | Panic button locations need to be checked
MLPD/Mono County Sherrif Collaboration | Alasdair | Reviewing the MOU and Flock | Cheryl and Jasmine have been working to update and broaden the scope of the MOU
Incident reporting | Security team | Lenna working with Verge on re-doing the system | Alasdair to get details to Cheryl prior to meeting with Lenna
MH Weapons Policy | Alasdair | Ordered new Signs | 6 new signs placed around the facility for "no weapons"
Psychiatric Emergency Team | Caitlin/Cheryl | Met with Mono County BH | November meeting had to be cancelled. Trying to reschedule next year
Safe Sitter Program Status | Jasmine | Jasmine unable to attend for update this week | Policy needs to be completed prior to sitter education
5150/1799 Holds | Jasmine | Jasmine unable to attend for update this week | Still finalizing policies
Panic Buttons for ED Providers | Alasdair/Mark | Alasdair working on setting up sales calls | Make sure we include ED staff as well as providers
EMTALA | Cheryl | Cheryl/Caitlin/Jasmine did an assessment. Working on a policy | Surveyors came and gave us a clean bill of health. Remove broad topic from Security Steering Committee
Signs and Entrance Issues | Cheryl | Signage/Phones at all entrances? | Can we put a buzzer on each enrtance for "medical emergency" help? Wayfinding maps at each door (perhaps including the ED phone number "if you need help")? Wayfinding arrows on the roads? Staff training to assist patients