## 10-14-24
Security Steering Committee
Date/Time: April 23, 25
Attendance: Caitlin, Zack, Mark, Alasdair, Jasmine, Larry, Ric
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Alasdair | i2i WPV Training in Healthstream
Security Supervisor/Guards Recruitment | Alasdair | Working on hiring per diem staff
Patient/Visitor/Staff Violence Events | Team | 4 incidents this month | Panic button locations need to be checked
MLPD/Mono County Sherrif Collaboration | Alasdair | Still working on MOU. | Dr. Walker is working with Jasmine to add to the existing MOU before sending it to the group
Incident reporting | Security team | Lenna working with Verge on re-doing the system | Alasdair to f/u with Stephanie on who follows up?
MH Weapons Policy | Alasdair | 6 new signs around facility. Still working with MCEMS and Mono County Legal on their policy
Psychiatric Emergency Team | Caitlin | Met with Mono County BH | November meeting had to be cancelled. Trying to reschedule next year
Safe Sitter Program Status | Jasmine | Can meet the need in the ED with current staffing. | Re-working the policy and getting staff education
5150/1799 Holds | Jasmine | 5150 policy sent out to other floor managers for review. Up to date on audits | trying to set up quarterly/monthly meeting with Mono County BH and MLPD for debrief
Panic Buttons for ED Providers | Alasdair/Mark | Had a meeting with kontakt.io and the ED staff. Still waiting for quotes. Also have two belt buttons for demo
EMTALA Signs and Entrance Issues | Cheryl | Signage/Phones at all entrances? | Can we put a buzzer on each enrtance for "medical emergency" help? Wayfinding maps at each door (perhaps including the ED phone number "if you need help")? Wayfinding arrows on the roads? Staff training to assist patients
NEW BUSINESS:
Lockdown Procedures | Maintenance | The existing buttons lockdown the hospital, but not everything on campus | Only security/Jeff/Admin can lockdown further buildings. Need a policy
Meeting schedule | Alasdair | Standing quarterly but also come up with a security steering checklist in the case of serious event