## 10-14-24
Security Steering Committee
Date/Time: April 23, 25
Attendance: Caitlin, Zack, Mark, Alasdair, Jasmine, Larry, Ric
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Alasdair | i2i WPV Training in Healthstream
Patient/Visitor/Staff Violence Events | Team | 3 events this month | Panic button locations need to be checked
MLPD/Mono County Sherrif Collaboration | Jasmine / Ric | Still working on MOU. | Ric reports progress has been made with Jasmine.
Incident reporting | Alasdair | Lenna working with Verge on re-doing the system | Compliance
MH Weapons Policy | Alasdair | 6 new signs around facility. Still working with MCEMS and Mono County Legal on their policy
Psychiatric Emergency Team | Caitlin | Met with Mono County BH | November meeting had to be cancelled. Trying to reschedule next year
Safe Sitter Program Status | Jasmine | Can meet the need in the ED with current staffing. | Re-working the policy and getting staff education
5150/1799 Holds | Jasmine | 5150 policy sent out to other floor managers for review. Up to date on audits | trying to set up quarterly/monthly meeting with Mono County BH and MLPD for debrief
Panic Buttons for ED Providers | Alasdair/Mark | Had a meeting with kontakt.io and the ED staff. Still waiting for quotes. Also have two belt buttons for demo
Lockdown Procedures | Maintenance | The existing buttons lockdown the hospital, but not everything on campus | Only security/Jeff/Admin can lockdown further buildings. Need a policy
Panic Button Alerts | Alasdair | Review the Bishop incident and the concerns that the panic button has an audible alert
Metal detectors | Mark/Alasdair | Meeting with architects to plan e-building entrance | Alasdair to f/u with Antonette on wands