## 8-13-24
Security Steering Committee
Date/Time: August 13 2024
Attendance: Caitlin, Zack, Mark, Alasdair, Cheryl
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Mark | MOAB training scheduled for September 10-12
Security Supervisor/Guards Recruitment | Alasdair | Hired a supervisor and one guard. Still working on filling out the staff for 24/7 coverage
Security Office Move to Triage Window | Alasdair | Working with Larry when he returns from leave to set up
Security Supervisor Move to A1 Window | Alasdair | Interpreters are moving out of their space and over to L&D2 on Wednesday. Once that's done, Jane can move her staff out of the office right there and then Larry can move in
Patient/Visitor/Staff Violence Events | Team | None new reported this period
MLPD/Mono County Sherrif Collaboration | Alasdair | Met with MLPD, meeting with Mono County Sheriff this week | Cheryl reviewing MOU with law enforcement.
Incident reporting | Security team | Since need to track all incidents, and Verge has existing stigma, have all incidents sent to security, who can follow up as well as add to Verge | Alasdair to discuss with Larry when he returns from medical leave
MH Weapons Policy | Alasdair | Can we improve signage? What about patients brought in by Mono County EMS | Alasdair to discuss with Chief Bullock of Mono County EMS to find out what their policy is prior to bringing patients to the ED
MLPD access to cameras | Alasdair | How do get MLPD access to live camera feed. | Alasdair looking into body cams for security and whether they can give live feed to PD, because existing cameras cannot be turned on and off in an ad hoc basis
Psychiatric Emergency Team |  | Can we work with Mono County Behavioral Health to help them set up a PET team | Caitlin to set up a meeting with the County
Safe Sitter Program Status | Jasmine | Jasmine unable to attend for update this week
5150/1799 Holds | Jasmine | Jasmine unable to attend for update this week