## 9-9-24
Security Steering Committee
Date/Time: September 9, 24
Attendance: Caitlin, Zack, Mark, Alasdair, Cheryl
Agenda Item | Owner | Status/Notes | Follow Up
De-escalation Training | Mark | MOAB training scheduled for September 10-12 | Moab training scheduled for this week
Security Supervisor/Guards Recruitment | Alasdair | Hired a supervisor and one guard. Still working on filling out the staff for 24/7 coverage | We have now hired two security guards and are working to hire two more.
Security Office Move to Triage Window | Alasdair | Working with Larry when he returns from leave to set up | This is complete
Security Supervisor Move to A1 Window | Alasdair | Interpreters are moving out of their space and over to L&D2 on Wednesday. Once that's done, Jane can move her staff out of the office right there and then Larry can move in | This is complete
Patient/Visitor/Staff Violence Events | Team | None new reported this period | One incident in the ED that has not yet been reported in Verge
MLPD/Mono County Sherrif Collaboration | Alasdair | Met with MLPD, meeting with Mono County Sheriff this week | Jasmine and Cheryl to do an internal review prior to updating the MOU with external agencies
Incident reporting | Security team | Since need to track all incidents, and Verge has existing stigma, have all incidents sent to security, who can follow up as well as add to Verge | Alasdair to discuss with Larry when he returns from medical leave
MH Weapons Policy | Alasdair | Can we improve signage? What about patients brought in by Mono County EMS | Alasdair to discuss with Chief Bullock of Mono County EMS to find out what their policy is prior to bringing patients to the ED
MLPD access to cameras | Alasdair | How do get MLPD access to live camera feed. | The team think that this should be pushed down the priority list and instead to focus on preventantive measures
Psychiatric Emergency Team |  | Can we work with Mono County Behavioral Health to help them set up a PET team | Caitlin has a meeting set up and report back next meeting
Safe Sitter Program Status | Jasmine | Jasmine unable to attend for update this week | Policy needs to be completed prior to sitter education
5150/1799 Holds | Jasmine | Jasmine unable to attend for update this week | Still finalizing policies
Ring Cam in the ED | Jasmine | It is operational and working as intended